## WBS
| Task Description | Deliverable | Estimated Time | Resources
1 | Program Registration & Attendance Data Hub | Yes | 272
Sprint 0: Initiation and Planning ¦ Sep 24 – Oct 19 ¦ Complete
1.1 | SWE 277P Assignment 1: Team Statement (Oct 6) | Yes | 8 | All team
1.2 | SWE 277P Assignment 2: MOV (Oct 13) | Yes | 8 | All team
1.3 | SWE 276P: Project Scope and High-Level Design report (Oct 16) | Yes | 16 | All team
1.4 | SWE 277P Assignment 3: Business Case (Oct 20) | Yes | 8 | All team
1.5 | SWE 277P Assignment 4: Project Charter (Oct 20) | Yes | 8 | All team
1.6 | Sponsor meetings and requirements (Oct 7, Oct 14) | No | 12 | All team
1.7 | Milestone: scope, MOV, business case and charter submitted | No | 0
Sprint 1: MVP Build ¦ Oct 20 – Nov 2 ¦ Current sprint
1.8 | Sprint planning and MVP design spec | Yes | 5
1.8.1 | MVP design spec and build plans | No | 4 | Zhenyu Song
1.8.2 | Team GitHub repo and shared time log | No | 1 | Brandon Lau
1.9 | US-01 Upload an event export as-is (UP-01 – UP-14, UP-19) | Yes | 14
1.9.1 | Database schema and migrations | No | 2 | Brandon Lau
1.9.2 | CampusGroups and 12twenty adapters; detect the format from the headers | No | 4 | Molly Tran
1.9.3 | Duplicate-file protection and commit | No | 2 | Molly Tran
1.9.4 | Upload page and event details form | No | 4 | Jennifer Sun
1.9.5 | Tests: A1 (293 rows, 79 NetIDs) and A2 (a re-upload adds nothing) | No | 2 | Molly Tran
1.10 | US-02 Link the same person across events (UP-15, UP-16) | Yes | 4
1.10.1 | Identity linker (NetID, then email) and data-quality flags | No | 3 | Molly Tran
1.10.2 | Tests for the linker cases | No | 1 | Molly Tran
1.11 | US-03 Ask a question and see the SQL and the table (CH-01 – CH-22) | Yes | 13
1.11.1 | Chat graph and prompt, with follow-ups, clarifying questions and repairs | No | 4 | Zhenyu Song
1.11.2 | SQL guard: one read-only SELECT on one view | No | 2 | Zhenyu Song
1.11.3 | Read-only database view and role | No | 1 | Brandon Lau
1.11.4 | Chat page: question box, progress steps, answer card | No | 4 | Jennifer Sun
1.11.5 | Tests: A6 privacy and A8 harmful SQL | No | 2 | Zhenyu Song
1.12 | US-04 Manage AI models and result sharing (ST-01 – ST-10, CH-08, CH-09) | Yes | 5
1.12.1 | Encrypted AI model profiles, Test connection, sharing rules | No | 3 | Zhenyu Song
1.12.2 | Settings page and the share switch | No | 2 | Jennifer Sun
1.13 | US-05 Download results and see what was imported (CH-05, CH-06, DS-01 – DS-05) | Yes | 4
1.13.1 | Excel and CSV export with a formula guard; full-dataset export | No | 2 | Molly Tran
1.13.2 | Dataset page and download buttons | No | 2 | Jennifer Sun
1.14 | MVP verification against the MOV (A1 – A10) | Yes | 8
1.14.1 | Chatbot benchmark: 20 questions and 10 held-out | No | 2 | Zhenyu Song
1.14.2 | Acceptance run and question-to-Excel timing (A10) | No | 2 | Brandon Lau
1.14.3 | Walk the user stories and the sponsor's Oct 21 requests | No | 4 | Brandon Lau
1.15 | Coordination and sponsor communication | No | 19
1.15.1 | Sponsor meetings (Oct 21, Oct 28) | No | 8 | All team
1.15.2 | Verify the ZotGPT gateway (by Oct 28) | No | 2 | Zhenyu Song
1.15.3 | Send the sponsor the LLM credit request | No | 1 | Brandon Lau
1.15.4 | Code walkthrough: each owner reviews their module | No | 8 | All team
1.16 | Capstone midterm report and presentation (Oct 26) | Yes | 16
1.16.1 | Report sections | No | 8 | All team
1.16.2 | Slides and rehearsal | No | 8 | All team
1.17 | SWE 277P Assignment 5: Work Breakdown Structure (Oct 27) | Yes | 5
1.17.1 | WBS and estimates | No | 3 | Brandon Lau
1.17.2 | Project description and MOV update | No | 1 | Molly Tran
1.17.3 | Review and submit | No | 1 | Jennifer Sun
1.18 | Milestone: MVP passes A1–A10 except A7 (Oct 22); midterm delivered | No | 0
Sprint 2: Sponsor Demo and Backlog ¦ Nov 3 – Nov 16 ¦ Planned
1.19 | Mid-project demo to the sponsor (week 7) | Yes | 6
1.19.1 | Demo preparation and dry run | No | 2 | Brandon Lau
1.19.2 | Demo and feedback | No | 4 | All team
1.20 | B4 Warn when an event is uploaded twice; delete a committed import | Yes | 7
1.20.1 | Detect an existing event; replace or delete its rows | No | 4 | Molly Tran
1.20.2 | Warning in the upload preview; delete button | No | 3 | Jennifer Sun
1.21 | B1 Delete a conversation and set a retention period | Yes | 6
1.21.1 | Delete API and cleanup job | No | 3 | Zhenyu Song
1.21.2 | Retention setting table | No | 1 | Brandon Lau
1.21.3 | Delete button and retention choice | No | 2 | Jennifer Sun
1.22 | B2 Downloads page for AI results | Yes | 3
1.22.1 | API that lists answers | No | 1 | Zhenyu Song
1.22.2 | Downloads page | No | 2 | Jennifer Sun
1.23 | B3 Insights button on the Dataset page | Yes | 4
1.23.1 | Preset questions; re-run the benchmark | No | 3 | Zhenyu Song
1.23.2 | Insights button | No | 1 | Jennifer Sun
1.24 | Fixes from the sponsor's demo feedback (placeholder) | Yes | 8 | All team
1.25 | Sprint 2 planning and tracking | No | 13
1.25.1 | Record Sprint 1 actual hours; plan Sprint 2 | No | 2 | Brandon Lau
1.25.2 | Regression walk and user guide update | No | 3 | Molly Tran
1.25.3 | Weekly team syncs | No | 8 | All team
1.26 | Milestone: sponsor demo given; B1–B4 done | No | 0
Sprint 3: Handoff and Final Delivery ¦ Nov 17 – Dec 7 ¦ Planned
1.27 | Staff login (acceptance test A7) | Yes | 6
1.27.1 | Login backend and the A7 test | No | 4 | Molly Tran
1.27.2 | Login page | No | 2 | Jennifer Sun
1.28 | CI and installation at the GPSRC | Yes | 5
1.28.1 | GitHub Actions CI | No | 3 | Brandon Lau
1.28.2 | Install the Hub on the GPSRC computer | No | 2 | Brandon Lau
1.29 | Handoff documents and staff training | Yes | 5
1.29.1 | Update the handoff, setup and user guides | No | 3 | Molly Tran
1.29.2 | Training session for GPSRC staff | No | 2 | Zhenyu Song
1.30 | Final testing | No | 6
1.30.1 | Final acceptance run and benchmark | No | 2 | Zhenyu Song
1.30.2 | Regression walk and bug fixes | No | 4 | All team
1.31 | Final report, final demo (Dec 4) and Capstone Showcase (Dec 7) | Yes | 32
1.31.1 | Final report | No | 8 | All team
1.31.2 | Final presentation and demo | No | 12 | All team
1.31.3 | Capstone Showcase | No | 8 | All team
1.31.4 | Peer evaluations | No | 4 | All team
1.32 | Sprint 3 planning and meetings | No | 18
1.32.1 | Record Sprint 2 actual hours; plan Sprint 3 | No | 2 | Brandon Lau
1.32.2 | Weekly team syncs and sponsor meetings | No | 16 | All team
1.33 | Milestone: MOV met and the Hub handed over (Dec 4); showcase (Dec 7) | No | 0