## WBS
| Task Description | Deliverable | Estimated Time | Resources
1 | Program Registration & Attendance Data Hub | Yes | 410
Sprint 0: Initiation and Planning ¦ Sep 24 – Oct 19 (Weeks 1–4) ¦ Complete
1.1 | SWE 277P Assignment 1: Team Statement (due Oct 6) | Yes | 15
1.1.1 | Write the project description | No | 2 | Jennifer Sun
1.1.2 | Initial team plan: strengths, sponsor questions, learning list | No | 2 | Molly Tran
1.1.3 | Team ground rules | No | 2 | Brandon Lau
1.1.4 | Create the shared Google Drive folder and share it with the instructor and TA | No | 1 | Zhenyu Song
1.1.5 | Team bonding dinner (Oct 6) | No | 8 | All team
1.2 | Sponsor kickoff and requirements | No | 18
1.2.1 | Read the sponsor proposal and the sample exports | No | 3 | Jennifer Sun
1.2.2 | Prepare questions for the first sponsor meeting | No | 2 | Molly Tran
1.2.3 | Sponsor meeting Oct 7: current process and sample data | No | 4 | All team
1.2.4 | Sponsor meeting Oct 14: scope narrowed to import, one dataset and queries | No | 4 | All team
1.2.5 | Write up meeting notes and action items | No | 2 | Molly Tran
1.2.6 | Map the GPSRC data process and the Data Project template columns | No | 3 | Molly Tran
1.3 | SWE 277P Assignment 2: MOV (due Oct 13) | Yes | 6
1.3.1 | Six-step MOV draft: impact, value, metric, time frame | No | 2 | Molly Tran
1.3.2 | Explain how the MOV supports GPSRC's vision and mission | No | 2 | Jennifer Sun
1.3.3 | Discuss the MOV with the sponsor and record the outcome | No | 1 | Molly Tran
1.3.4 | Review and submit | No | 1 | Brandon Lau
1.4 | SWE 276P: Project Scope and High-Level Design report (due Oct 16) | Yes | 18
1.4.1 | Project overview, target users and stakeholders | No | 2 | Jennifer Sun
1.4.2 | Scope definition: boundaries, P0/P1/P2 features, assumptions | No | 4 | Zhenyu Song
1.4.3 | C4 context, container and component diagrams | No | 4 | Zhenyu Song
1.4.4 | Data model and import sequence diagrams | No | 3 | Brandon Lau
1.4.5 | Technology stack and design rationale | No | 3 | Zhenyu Song
1.4.6 | Edit, format as PDF and submit | No | 2 | Molly Tran
1.5 | Technology ramp-up | No | 12
1.5.1 | PostgreSQL, Alembic, Docker Compose and nginx | No | 3 | Brandon Lau
1.5.2 | React, MUI and TanStack Query | No | 3 | Jennifer Sun
1.5.3 | LangGraph, text-to-SQL and the LLM provider APIs | No | 3 | Zhenyu Song
1.5.4 | FastAPI and reading CSV and Excel exports | No | 3 | Molly Tran
1.6 | SWE 277P Assignment 3: Business Case (due Oct 20) | Yes | 8
1.6.1 | Executive summary and introduction | No | 2 | Brandon Lau
1.6.2 | Alternatives and their analysis (TCO, TBO, feasibility, risk) | No | 3 | Jennifer Sun
1.6.3 | Scoring model and recommendation | No | 2 | Molly Tran
1.6.4 | Final consistency check and submit | No | 1 | Zhenyu Song
1.7 | SWE 277P Assignment 4: Project Charter (due Oct 20) | Yes | 7
1.7.1 | Stakeholder table, project description and MOV | No | 2 | Brandon Lau
1.7.2 | Scope and schedule summary | No | 2 | Molly Tran
1.7.3 | Resources and cost estimate | No | 2 | Jennifer Sun
1.7.4 | Title page, table of contents and formatting | No | 1 | Brandon Lau
1.8 | Team meetings and coordination | No | 25
1.8.1 | Weekly check-ins with the instructor and TA (Oct 6, Oct 13) | No | 8 | All team
1.8.2 | Team scope discussions (Oct 15, Oct 17) | No | 8 | All team
1.8.3 | Team meeting Oct 19: split document edits, assign roles, plan the midterm | No | 8 | All team
1.8.4 | Set up the team chat, meeting cadence and shared documents | No | 1 | Molly Tran
1.9 | Milestone: scope, MOV, business case and charter submitted (Oct 20) | No | 0
Sprint 1: MVP Build ¦ Oct 20 – Nov 2 (Weeks 4–6) ¦ Current sprint
1.10 | Sprint 1 planning and MVP design spec | Yes | 7
1.10.1 | Write the MVP design spec (decisions D1–D10, data model, chatbot, acceptance tests A1–A10) | No | 3 | Zhenyu Song
1.10.2 | Break the spec into session plans S2–S6; write CLAUDE.md and PROGRESS.md | No | 2 | Zhenyu Song
1.10.3 | Set up the team's private GitHub repo and invite every member | No | 1 | Brandon Lau
1.10.4 | Sprint planning: assign an owner to each user story | No | 1 | Brandon Lau
1.11 | US-01 Upload an event export as-is (UP-01 – UP-10, UP-19) | Yes | 14
1.11.1 | Map CampusGroups and 12twenty columns to the GPSRC layout | No | 2 | Molly Tran
1.11.2 | Database schema and migrations (import_file, event, person, attendance, flags) | No | 2 | Brandon Lau
1.11.3 | CampusGroups and 12twenty adapters | No | 3 | Molly Tran
1.11.4 | Detect the source from the headers; reject unknown formats and list missing columns | No | 1 | Molly Tran
1.11.5 | Duplicate-file protection (file hash and content hash) | No | 1 | Molly Tran
1.11.6 | Upload page: drop zone, preview, Duplicate and Rejected cards | No | 3 | Jennifer Sun
1.11.7 | Tests: A1 (293 rows, 79 NetIDs) and A2 (a re-upload adds nothing) | No | 2 | Molly Tran
1.12 | US-02 Enter event details before commit (UP-11 – UP-14) | Yes | 5
1.12.1 | Prefill the event name from the file name and the date from the Registration UID | No | 1 | Molly Tran
1.12.2 | Event form with term check and required fields | No | 2 | Jennifer Sun
1.12.3 | Commit in one transaction; discard a pending import | No | 1 | Molly Tran
1.12.4 | Keep pending imports across pages and reloads | No | 1 | Jennifer Sun
1.13 | US-03 Link the same person across events (UP-15, UP-16) | Yes | 4
1.13.1 | Identity linker: NetID first, then email; flag conflicts | No | 2 | Molly Tran
1.13.2 | Data-quality flags and their counts in the preview | No | 1 | Molly Tran
1.13.3 | Tests: linker cases; the November Bagel Breakfast row links by email | No | 1 | Molly Tran
1.14 | US-04 Ask a question and see the SQL and the table (CH-01, CH-04, CH-11, CH-19) | Yes | 11
1.14.1 | Read-only attendance_view and chatbot_ro role with a 5 s timeout | No | 1 | Brandon Lau
1.14.2 | LangGraph chat graph and SQL-generation prompt | No | 3 | Zhenyu Song
1.14.3 | Streaming API (SSE) and saved conversations | No | 2 | Zhenyu Song
1.14.4 | Chat page: question box, progress steps, answer card, SQL and table | No | 3 | Jennifer Sun
1.14.5 | Recent questions in the side nav; reopen and re-run old answers | No | 1 | Jennifer Sun
1.14.6 | Tests: graph integration tests with a scripted model | No | 1 | Zhenyu Song
1.15 | US-05 Follow-ups, clarifying questions and repairs (CH-02, CH-03, CH-12, CH-13, CH-22) | Yes | 4
1.15.1 | Conversation history (questions and SQL only) for follow-ups | No | 1 | Zhenyu Song
1.15.2 | Clarifying questions and the repair loop (up to 3 tries) | No | 2 | Zhenyu Song
1.15.3 | Clarification bubble and Retry in the chat page | No | 1 | Jennifer Sun
1.16 | US-06 Keep the data safe from generated SQL (A6, A8) | Yes | 4
1.16.1 | SQL guard: one SELECT on attendance_view, function allow-list, row limit | No | 2 | Zhenyu Song
1.16.2 | Read-only executor that always rolls back, and the error sanitizer | No | 1 | Zhenyu Song
1.16.3 | Tests: A8 harmful SQL and A6 privacy with a recording model | No | 1 | Zhenyu Song
1.17 | US-07 Choose whether the AI sees the results (CH-08, CH-09) | Yes | 3
1.17.1 | Per-model ceiling plus per-question switch, decided on the server | No | 1 | Zhenyu Song
1.17.2 | AI summary from capped rows, or a local summary | No | 1 | Zhenyu Song
1.17.3 | Switch in the question box, its help text and the caution line | No | 1 | Jennifer Sun
1.18 | US-08 Manage AI models in Settings (ST-01 – ST-10, CH-10, CH-17, CH-21) | Yes | 5
1.18.1 | Encrypted API keys, provider presets and Test connection | No | 2 | Zhenyu Song
1.18.2 | Settings page: add, test, edit, set default, delete | No | 2 | Jennifer Sun
1.18.3 | Walk the Settings stories ST-01 – ST-10 | No | 1 | Molly Tran
1.19 | US-09 Download results as Excel or CSV (CH-05, CH-06, DS-02) | Yes | 5
1.19.1 | Excel and CSV writers with a formula guard; full dataset in the 19-column layout | No | 2 | Molly Tran
1.19.2 | Export of a chat result with a row cap | No | 1 | Zhenyu Song
1.19.3 | Download buttons and the "This file stops at N rows" notice | No | 1 | Jennifer Sun
1.19.4 | Time question to downloaded Excel (A10, under 60 s) | No | 1 | Brandon Lau
1.20 | US-10 See what has been imported (DS-01 – DS-05) | Yes | 2
1.20.1 | Imports list API with the rows each file added | No | 1 | Molly Tran
1.20.2 | Dataset page: file list, Pending link, full download | No | 1 | Jennifer Sun
1.21 | US-11 Move around the app on a laptop screen (SH-01 – SH-07) | Yes | 4
1.21.1 | UCI blue-and-gold redesign: side nav and header bar (artboards A2, D2, E1) | No | 3 | Jennifer Sun
1.21.2 | Page not found, Not connected and reload pages; keyboard focus rings | No | 1 | Jennifer Sun
1.22 | MVP verification against the MOV (A1 – A10, SP-01 – SP-14) | Yes | 10
1.22.1 | Chatbot benchmark: 20 questions and 10 held-out; tune the prompt | No | 2 | Zhenyu Song
1.22.2 | Full acceptance run (acceptance.sh) | No | 1 | Brandon Lau
1.22.3 | Walk the 63 user stories and log the findings | No | 3 | Brandon Lau
1.22.4 | Walk the sponsor's Oct 21 requests (SP-01 – SP-14) | No | 2 | Brandon Lau
1.22.5 | First drafts: setup guide, user guide, data dictionary, known limitations | No | 2 | Molly Tran
1.23 | Project management and sponsor communication | No | 20
1.23.1 | Sponsor meeting Oct 21: confirm the three success metrics and the query needs | No | 4 | All team
1.23.2 | Email the sponsor the LLM credit request ($100–200) | No | 1 | Brandon Lau
1.23.3 | Verify the ZotGPT gateway: base URL, JSON mode, model names (by Oct 28) | No | 2 | Zhenyu Song
1.23.4 | Sponsor meeting Oct 28 | No | 4 | All team
1.23.5 | Code walkthrough: each owner reviews their module in the team repo | No | 8 | All team
1.23.6 | Start the shared time log (actual hours per WBS ID) | No | 1 | Brandon Lau
1.24 | Capstone midterm report and presentation (due Oct 26) | Yes | 16
1.24.1 | Report: project overview, import pipeline and MOV status | No | 2 | Molly Tran
1.24.2 | Report: database and deployment | No | 2 | Brandon Lau
1.24.3 | Report: UI walkthrough with screenshots | No | 2 | Jennifer Sun
1.24.4 | Report: chatbot design and benchmark results | No | 2 | Zhenyu Song
1.24.5 | Slides and Sunday rehearsal (1–2 minutes each) | No | 8 | All team
1.25 | SWE 277P Assignment 5: Work Breakdown Structure (due Oct 27) | Yes | 6
1.25.1 | Project description and MOV update | No | 1 | Brandon Lau
1.25.2 | WBS: sprints, tasks, owners and estimates | No | 3 | Brandon Lau
1.25.3 | Estimation techniques | No | 1 | Jennifer Sun
1.25.4 | Review and submit | No | 1 | Zhenyu Song
1.26 | Milestone: MVP passes A1–A10 except A7 (Oct 22); midterm delivered (Oct 26) | No | 0
Sprint 2: Sponsor Demo and Backlog Features ¦ Nov 3 – Nov 16 (Weeks 6–8) ¦ Planned
1.27 | Sprint 2 planning and tracking | No | 10
1.27.1 | Record Sprint 1 actual hours; plan Sprint 2 (WBS update) | No | 2 | Brandon Lau
1.27.2 | Weekly team syncs (Nov 3, Nov 10) | No | 8 | All team
1.28 | Mid-project demo to the sponsor (week 7) | Yes | 10
1.28.1 | Set the attendance-source note on main's 12twenty events (SF-3) | No | 1 | Brandon Lau
1.28.2 | Rebuild the main stack; click through every page with a real AI model | No | 1 | Brandon Lau
1.28.3 | Try an Excel and a CSV export in Safari | No | 1 | Jennifer Sun
1.28.4 | Demo script and dry run (README story order) | No | 2 | Brandon Lau
1.28.5 | Demo to the sponsor and collect feedback | No | 4 | All team
1.28.6 | Ask the sponsor: result sharing (D1), waitlisted registrants, postdocs as students, Notes wording | No | 1 | Brandon Lau
1.29 | B4 Warn when an event is uploaded a second time (bug, high; SF-1) | Yes | 8
1.29.1 | Design draft: preview warning with Replace, Add anyway and Cancel | No | 1 | Jennifer Sun
1.29.2 | Detect an existing event with the same name and term, or mostly the same people | No | 2 | Molly Tran
1.29.3 | Preview warning and the three choices | No | 2 | Jennifer Sun
1.29.4 | Replace an event's rows in one transaction | No | 2 | Molly Tran
1.29.5 | Test the 35-row then 38-row download; Chat must answer 38 | No | 1 | Jennifer Sun
1.30 | Delete a committed import (handoff backlog; second half of the B4 fix) | Yes | 4
1.30.1 | Delete API: remove the event, its rows and its flags | No | 2 | Molly Tran
1.30.2 | Delete button with a confirm step on the Dataset page | No | 1 | Jennifer Sun
1.30.3 | Tests | No | 1 | Molly Tran
1.31 | B1 Delete a conversation and set a retention period | Yes | 9
1.31.1 | Design draft; ask the sponsor about UCI retention and the query log | No | 1 | Zhenyu Song
1.31.2 | Delete API for a conversation (its turns go with it) | No | 1 | Zhenyu Song
1.31.3 | App settings table and retention setting (never, 6, 3 or 1 month) | No | 2 | Brandon Lau
1.31.4 | Cleanup job that deletes conversations past the retention period | No | 2 | Zhenyu Song
1.31.5 | Delete in Recent questions; retention choice in Settings | No | 2 | Jennifer Sun
1.31.6 | Tests | No | 1 | Zhenyu Song
1.32 | B2 Downloads page for AI results | Yes | 5
1.32.1 | Design draft: which answers to list; name and icon in the side nav | No | 1 | Jennifer Sun
1.32.2 | API that lists answers (question, date, row count) | No | 1 | Zhenyu Song
1.32.3 | Downloads page with Excel and CSV buttons | No | 2 | Jennifer Sun
1.32.4 | Tests | No | 1 | Jennifer Sun
1.33 | B3 Insights button on the Dataset page | Yes | 4
1.33.1 | Spike: how the chatbot answers an open "insights" question | No | 1 | Zhenyu Song
1.33.2 | Preset question set: by event, by school, repeat attendees, by term | No | 1 | Zhenyu Song
1.33.3 | Insights button opens a new chat and sends the set | No | 1 | Jennifer Sun
1.33.4 | Re-run the benchmark (main and held-out) | No | 1 | Zhenyu Song
1.34 | Fixes from the sponsor walkthrough (SF-2, SF-4, SF-5, SF-9) | Yes | 5
1.34.1 | SF-2: warn at upload when the event date is blank | No | 1 | Molly Tran
1.34.2 | SF-4: write the local summary as a sentence when sharing is off | No | 2 | Zhenyu Song
1.34.3 | SF-5: refer to people by name in readings; re-run the benchmark | No | 1 | Zhenyu Song
1.34.4 | SF-9: title-case the export headers and name the sheet | No | 1 | Molly Tran
1.35 | AI provider funding and second benchmark (A4) | No | 3
1.35.1 | Set up the funded provider account with spending limits | No | 1 | Zhenyu Song
1.35.2 | Benchmark a second provider (ZotGPT or OpenAI) | No | 2 | Zhenyu Song
1.36 | Import improvements (handoff backlog) | Yes | 6
1.36.1 | Edit the event details of a committed import | No | 2 | Molly Tran
1.36.2 | Attach a second file to an existing event | No | 2 | Molly Tran
1.36.3 | Edit and attach controls on the Dataset page | No | 2 | Jennifer Sun
1.37 | Regression check and docs | No | 5
1.37.1 | Re-walk the user stories that B1–B4 touch | No | 2 | Jennifer Sun
1.37.2 | Full acceptance run and benchmark | No | 1 | Brandon Lau
1.37.3 | Update the user guide and known limitations for B1–B4 | No | 2 | Brandon Lau
1.38 | SWE 277P schedule and cost assignments (placeholder; dates TBA) | Yes | 6
1.38.1 | Project schedule from this WBS | No | 3 | Brandon Lau
1.38.2 | Cost estimate from the WBS hours | No | 2 | Brandon Lau
1.38.3 | Review | No | 1 | Brandon Lau
1.39 | Milestone: sponsor demo given; B1–B4 built and tested | No | 0
Sprint 3: Hardening, Handoff and Final Delivery ¦ Nov 17 – Dec 7 (Weeks 8–10, showcase) ¦ Planned
1.40 | Sprint 3 planning and meetings | No | 18
1.40.1 | Record Sprint 2 actual hours; plan Sprint 3 | No | 2 | Brandon Lau
1.40.2 | Weekly team syncs (Nov 17, Nov 24, Dec 1) | No | 8 | All team
1.40.3 | Sponsor meetings (Nov 18, Dec 2; Nov 25 skipped for Thanksgiving) | No | 8 | All team
1.41 | Staff login (handoff backlog; acceptance test A7) | Yes | 7
1.41.1 | Confirm with the sponsor: one staff account or several | No | 1 | Brandon Lau
1.41.2 | AUTH_MODE=password: password hash, login and logout routes, httpOnly cookie | No | 3 | Molly Tran
1.41.3 | Login page behind AuthGate; handle 401 in the API client | No | 2 | Jennifer Sun
1.41.4 | A7 acceptance test: no data without signing in | No | 1 | Molly Tran
1.42 | Prepare for hosting on a UCI OIT server (handoff checklist) | Yes | 7
1.42.1 | Ask OIT about data classification, hosting and allowed AI providers | No | 1 | Brandon Lau
1.42.2 | HTTPS at nginx; publish only the HTTPS port | No | 2 | Brandon Lau
1.42.3 | Secret storage and API key rotation (changing HUB_SECRET_KEY) | No | 2 | Brandon Lau
1.42.4 | Scheduled pg_dump backups and a restore test | No | 2 | Brandon Lau
1.43 | CI on the team's GitHub repo | No | 3
1.43.1 | GitHub Actions: ruff, pytest, Vitest, oxlint and build | No | 2 | Brandon Lau
1.43.2 | Run the Playwright e2e test in CI | No | 1 | Brandon Lau
1.44 | ZotGPT support | No | 3
1.44.1 | Adjust the JSON-mode detection or merge user messages if ZotGPT needs it | No | 2 | Zhenyu Song
1.44.2 | Benchmark ZotGPT (main and held-out) | No | 1 | Zhenyu Song
1.45 | P1 features from the extension points (pending sponsor priority) | Yes | 14
1.45.1 | F11 filter table on the Dataset page (SF-8): route | No | 1 | Molly Tran
1.45.2 | F11 filter table on the Dataset page (SF-8): DataGrid page | No | 3 | Jennifer Sun
1.45.3 | F12 data-quality view: list and resolve flags, fill blank fields (API) | No | 2 | Molly Tran
1.45.4 | F12 data-quality view: list and resolve flags, fill blank fields (page) | No | 2 | Jennifer Sun
1.45.5 | F14 saved queries: saved_query table and one-click run | No | 2 | Zhenyu Song
1.45.6 | F14 saved queries: Saved list in the side nav | No | 1 | Jennifer Sun
1.45.7 | F15 historical import: gpsrc_sheet adapter and migration | No | 3 | Molly Tran
1.46 | Final testing and acceptance | No | 9
1.46.1 | Final acceptance run A1–A10, including A7 | No | 2 | Brandon Lau
1.46.2 | Regression walk of all user stories | No | 3 | Zhenyu Song
1.46.3 | Bug-fix buffer for the regression walk | No | 4 | All team
1.47 | Handoff to the GPSRC | Yes | 9
1.47.1 | Update the handoff, setup and user guides, data dictionary and known limitations | No | 3 | Molly Tran
1.47.2 | Regenerate the screenshots | No | 1 | Jennifer Sun
1.47.3 | Install the Hub on the GPSRC computer (Docker Desktop) | No | 2 | Brandon Lau
1.47.4 | Training session for GPSRC staff and student workers | No | 2 | Zhenyu Song
1.47.5 | Hand over the repository and the key-handling steps | No | 1 | Brandon Lau
1.48 | Final report, final demo (Dec 4) and Capstone Showcase (Dec 7) | Yes | 36
1.48.1 | Final report: import pipeline and MOV results | No | 2 | Molly Tran
1.48.2 | Final report: database, deployment and project management | No | 2 | Brandon Lau
1.48.3 | Final report: user interface | No | 2 | Jennifer Sun
1.48.4 | Final report: chatbot, privacy and benchmark | No | 2 | Zhenyu Song
1.48.5 | Final report: assemble, edit and submit | No | 2 | Jennifer Sun
1.48.6 | Final presentation slides and rehearsal | No | 8 | All team
1.48.7 | Final demo to the sponsor and instructor (Dec 4) | No | 4 | All team
1.48.8 | Showcase poster | No | 2 | Jennifer Sun
1.48.9 | Capstone Showcase booth and live demo (Dec 7) | No | 8 | All team
1.48.10 | Peer evaluations | No | 4 | All team
1.49 | Milestone: MOV met and the Hub handed over (Dec 4); showcase (Dec 7) | No | 0
Post-capstone backlog (not scheduled; not counted in the capacity check)
1.50 | Items left for the next team or a later phase | No | 10
1.50.1 | F16 multiple staff accounts and an admin page (needs login first) | No | 3 | Molly Tran
1.50.2 | Native Anthropic or Gemini connector | No | 3 | Zhenyu Song
1.50.3 | Attendance roster by school to measure service gaps (SF-7; new data source) | No | 4 | Molly Tran

## Effort Summary
Effort by person and sprint (person-hours)
Computed from the WBS sheet. Rows owned by "All team" are split evenly across the four members.
Assumptions (blue = input)
Team members | 4
Hours per person per week (project charter) | 10
Person | Role | Sprint 0 | Sprint 1 | Sprint 2 | Sprint 3 | Total
Brandon Lau | Database / DevOps | 24 | 26 | 21 | 31 | 102
Jennifer Sun | Frontend | 27 | 29 | 20 | 26 | 102
Molly Tran | Backend / Data Import | 32 | 29 | 16 | 26 | 103
Zhenyu Song | AI / Chatbot | 26 | 36 | 18 | 23 | 103
Total |  | 109 | 120 | 75 | 106 | 410
Check: sum of the WBS task rows |  | 109 | 120 | 75 | 106 | 410
Weeks in the sprint |  | 3.5 | 2 | 2 | 2.5 | 10
Capacity (weeks × members × hours per week) |  | 140 | 80 | 80 | 100 | 400
Load (planned ÷ capacity) |  | 77.86% | 150% | 93.75% | 106% | 102.5%
Notes
Estimated Time is in person-hours of human work: planning, specifying, reviewing AI-generated code, testing and writing.
Sprint 1 is over capacity on purpose: the MVP the charter planned for weeks 5–9 was built in Sprint 1 with AI-assisted development.
Sprints 2 and 3 use the time this freed for the backlog (docs/backlog.md) and the handoff items (docs/handoff.md).
The post-capstone backlog at the end of the WBS sheet is not counted here.
From Sprint 2 on, the WBS gets an Actual Time column filled from the team's time log.